## Slide 1: Project Integration Management
Chapter 4

## Slide 2: The Key to Overall Project Success: Good Project Integration Management
Project managers must coordinate all of the other knowledge areas throughout a project’s life cycle
Project integration management is not the same thing as software integration

## Slide 3: Project Integration Management Processes
Process Group | Integration Management Process | Major Output
Initiating | Developing the project charter | Project Charter
Planning | Developing the project management plan | Project Management Plan
Executing | Directing and managing project work | Deliverables, work performance info, change requests
Monitoring and Controlling | (1) Monitor/Control Project Work (2) Perform Integrated Change Control | (1) Change Requests (2) Status updates
Closing | Close Project/Phase | Product Transition

## Slide 4: Project Integration Management Summary

## Slide 5: Strategic Planning and Project Selection
Strategic planning involves determining long-term objectives, predicting future trends, and projecting the need for new products and services
Organizations often perform a SWOT analysis

## Slide 6: Figure 4-3. Information Technology Planning Process

## Slide 7: Learning from Project Success
Only one in seven product concepts comes to fruition. Why is it that some companies, like Proctor & Gamble, Johnson and Johnson, Hewlett Packard, and Sony are consistently successful in NPD? Because they use a disciplined, systematic approach to NPD projects based on best practices
Four important forces behind NPD success include the following:
  A product innovation and technology strategy for the business
  Resource commitment and focusing on the right projects, or solid portfolio management
  An effective, flexible and streamlined idea-to-launch process
  The right climate and culture for innovation, true cross-functional teams, and senior management commitment to NPD

## Slide 8: Methods for Selecting Projects
There are usually more projects than available time and resources to implement them
Methods for selecting projects
  Feasibility Study – can it even be done?
  Benefits Contributions
  Economics Models
  Scoring Models

## Slide 9: Method: Focusing on Broad Organizational Needs
It is often difficult to provide strong justification for many IT projects, but everyone agrees they have a high value
Three important criteria for projects

## Slide 10: Method: Categorizing IT Projects
One categorization is whether the project addresses
  a problem
  an opportunity, or
  a directive

## Slide 11: Methods: Financial Analysis of Projects
Three primary methods for determining the projected financial value of projects:
  Net present value (NPV) analysis
  Return on investment (ROI)
  Payback analysis

## Slide 12: Net Present Value Analysis
Net present value (NPV) analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time

## Slide 13: NPV Calculations
Determine estimated costs and benefits for the life of the project and the products it produces
Determine the discount rate (check with your organization on what to use)
Calculate the NPV
NPV = At / (1+r)2
= Amount of Cash Flow
t = year of the cash flow
r = discount rate

## Slide 14: Return on Investment
Return on investment (ROI) is calculated by subtracting the project costs from the benefits and then dividing by the costs
  ROI = (total discounted benefits - total discounted costs) / discounted costs

## Slide 15: JWD Consulting NPV Example
Discount Rate: 8%
Costs:
Y0: $140,000
Y1 - 3: $40,000
Benefits:
Y0: $0
Y1 - 3: $200,000
Year 0: discount factor = 1/(1+0.08)0 = 1
Year 1: discount factor = 1/(1+0.08)1 = 0.93
Notes: Actually run through this in class with students
WHAT ARE THESE BASED ON => ESTIMATES

## Slide 16: JWD Consulting NPV Example
Note: See the template called business_case_financials.xls

## Slide 17: Payback Analysis
The payback period is the amount of time it will take to recoup, in the form of net cash inflows, the total dollars invested in a project

## Slide 18: Method: Weighted Scoring Model
A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria
    Identify criteria important to the project selection process
    Assign weights (percentages) to each criterion so they add up to 100%
    Assign scores to each criterion for each project
    Multiply the scores by the weights and get the total weighted scores

## Slide 19: Sample Weighted Scoring Model Criteria
Criteria:
  Supports key business objectives (25%)
  Strong internal sponsor (15%)
  Strong customer support (10%)
  One year or less implementation (20%)
  Positive NPV (30%)

## Slide 20: Sample Weighted Scoring Model - Projects
  Project 1
    A director has been charged with finding ways to address the strategic goals for technology set at the recent board meeting. He has suggested an upgrade to the system that will take about a year to complete. Because their system is currently quite complex, this is based on estimates which could change frequently. He has support from many executives to move forward and, if they stay on budget, there will be a positive NPV.
  Project 2
    A manager wants to create an internal site to track project success and failures. She estimates a 6 month timeline with minimal risk of running longer or costing more than estimates. For right now, the NPV is negative.

## Slide 21: Sample Weighted Scoring Model - Projects
  Project 3
    New system implementation that may take 18 months to complete. This implementation is being supported by the CIO and executives as it will enable the company to meet the new strategy to become a leader in customer service. The payback period is 4 years but it will result in positive NPV.

## Slide 22: Method: Implementing a Balanced Scorecard
A balanced scorecard is a methodology that converts an organization’s value drivers, such as customer service, innovation, operational efficiency, and financial performance, to a series of defined metrics

## Slide 23: Additional Methods
Scoring
Opportunity Costs
Six Sigma

## Slide 24: Initiating Process Group: Developing a Project Charter
A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management
Key Output of Project Integration: Signed Charter

## Slide 25: Inputs for Developing a Project Charter

## Slide 26: Table 4-1. Project Charter (cont.)

## Slide 27: Planning Process Group: Develop Project Management Plan
A project management plan is a document used to coordinate all project planning documents and help guide a project’s execution and control
Common Elements:
  Introduction or overview of the project
  Description of how the project is organized
  Management and technical processes
  Work to be done, schedule, and budget info

## Slide 28: Table 4-2. Sample Contents for a Software Project Management Plan (SPMP)

## Slide 29: Successful Planning
"The winners clearly spell out what needs to be done in a project, by whom, when, and how. For this they use an integrated toolbox, including PM tools, methods, and techniques…If a scheduling template is developed and used over and over, it becomes a repeatable action that leads to higher productivity and lower uncertainty. Sure, using scheduling templates is neither a breakthrough nor a feat. But laggards exhibited almost no use of the templates. Rather, in constructing schedules their project managers started with a clean sheet, a clear waste of time.“*
*Milosevic, Dragan and And Ozbay. “Delivering Projects: What the Winners Do.” Proceedings of the Project Management Institute Annual Seminars & Symposium (November 2001).

## Slide 30: Executing Process Group: Directing and Managing Project Work
Involves managing and performing the work described in the project management plan
Project planning and execution are intertwined and inseparable activities

## Slide 31: Providing Leadership and a Supportive Culture
Project managers must lead by example to demonstrate the importance of creating and then following good project plans

## Slide 32: Capitalizing on Product, Business, and Application Area Knowledge
It is often helpful for IT project managers to have prior technical experience
Small vs. Large Projects

## Slide 33: Project Execution Tools and Techniques
Expert judgment
Meetings
Project management information systems

## Slide 34: Monitoring and Controlling Project Work
Changes are inevitable on most projects, so it’s important to develop and follow a process to monitor and control changes
Monitoring project work includes collecting, measuring, and disseminating performance information
A baseline is the approved project management plan plus approved changes

## Slide 35: Performing Integrated Change Control
Three main objectives are:
  Influencing the factors that create changes to ensure that changes are beneficial
  Determining that a change has occurred
  Managing actual changes as they occur

## Slide 36: Change Control on Information Technology Projects
Former view & Problems
Modern view & Solution

## Slide 37: Change Control System
A change control system is a formal, documented process that describes when and how official project documents and work may be changed
Describes who is authorized to make changes and how to make them

## Slide 38: Change Control Board (CCB)
A change control board is a formal group of people responsible for approving or rejecting changes on a project
CCBs provide guidelines for preparing change requests, evaluate change requests, and manage the implementation of approved changes

## Slide 39: Configuration Management
Configuration management ensures that the descriptions of the project’s products are correct and complete
Involves identifying and controlling the functional and physical design characteristics of products and their support documentation

## Slide 40: Table 4-3. Suggestions for Performing Integrated Change Control

## Slide 41: Closing Projects or Phases
To close a project or phase, you must finalize all activities and transfer the completed or cancelled work to the appropriate people
Main outputs include
  Final product, service, or result transition
  Organizational process asset updates

## Slide 42: Using Software to Assist in Project Integration Management
Several types of software can be used to assist in project integration management
  Project management software can pull everything together and show detailed and summarized information
  Business Service Management (BSM) tools track the execution of business process flows

## Slide 43: Chapter Summary
Project integration management involves coordinating all of the other knowledge areas throughout a project’s life cycle
Main processes include
  Develop the project charter
  Develop the project management plan
  Direct and manage project execution
  Monitor and control project work
  Perform integrated change control
  Close the project or phase