## Slide 1: Project Time Management
PMI Knowledge Areas

## Slide 2: Announcements
Project Deliverables
  Project – Integration Mgmt
  Project – Scope Mgmt (due Friday)
Exercise 2 – available Friday
Midterm Next Monday

## Slide 3: Importance of Project Schedules
Managers often cite delivering projects on time as one of their biggest challenges
Schedule issues are the main reason for conflicts on projects, especially during the second half of projects

## Slide 4: Project Time Management Processes
Process Group | Integration Management Process | Major Output
Planning | P1: Defining Activities | Activity List
 | P2: Sequence Activities | Project Schedule Network Diagram
 | P3: Estimate Activity Resources | Activity Resource Reqs.
 | P4: Estimate Activity Duration | Activity Duration Estimates
 | P5: Develop Schedule | Project Schedule
Monitoring and Controlling | MC1: Control Schedule | Work Performance Measuerments

## Slide 5: Project Time Management Summary

## Slide 6: P1: Defining Activities
An activity or task is an element of work normally found on the work breakdown structure (WBS) that has an expected duration, a cost, and resource requirements
Input
1) Scope Baseline 2) Enterprise Environment Factors 3) Organizational Process Assets
Tools/Techniques
1) Decomposition 2) Component Planning 3) Templates 4) Expert Judgment
Output
1) Activity List 2) Activity Attributes 3) Milestone List

## Slide 7: Activity Lists, Attributes & Milestones
An activity list is a tabulation of activities to be included on a project schedule that includes
  Activity attributes
A milestone is a significant event that normally has no duration
  Examples include obtaining customer sign-off on key documents or completion of specific products

## Slide 8: P2: Sequencing Activities
Involves reviewing activities and determining dependencies
A dependency or relationship is the sequencing of project activities or tasks
You must determine dependencies in order to use critical path analysis
Input
1) Activity List & Attributes 2) Milestone List 3) Scope Statement 4) Org Process Assets
Tools/Techniques
1) Determine Dependency 2) PDM 3) Apply Leads/Lags 4) Schedule Network templates
Output
1) Project Schedule Network Diagrams 2) Update Project Docs

## Slide 9: Network Diagrams
A network diagram is a schematic display of the logical relationships among, or sequencing of, project activities
Two main formats are the arrow and precedence diagramming methods

## Slide 10: Activity-on-arrow (AOA) or Arrow Diagramming Method (ADM)
Activities are represented by arrows
Nodes or circles are the starting and ending points of activities
Can only show finish-to-start dependencies

## Slide 11: Precedence Diagramming Method (PDM)
Activities are represented by boxes
Arrows show relationships between activities
More popular than ADM method and used by project management software
http://csb.uncw.edu/people/cummingsj/classes/MIS492/Exercises/SampleTime.mpp

## Slide 12: Figure 6-3. Task Dependency Types

## Slide 13: Reasons for Creating Dependencies
Mandatory dependencies (hard logic)
Discretionary dependencies (soft logic)
External dependencies

## Slide 14: P3: Estimating Activity Resources
A resource breakdown structure is a hierarchical structure that identifies the project’s resources by category and type
Input
1) Activity List & Attributes 2) Resource Calendars 3) Enterprise Factors 4) Org Process Assets
Output
1) Activity Resource Req 2) Resource Breakdown Structure 3) Updates to Project Docs
Tools/Techniques
1) Alternative Analysis 2) Bottom-up Estimating 3) Expert Judgment 4) PM Software 5) Estimating Data
Determine the resource requirements for each activity

## Slide 15: Estimating Activity Resources
Consider important issues in estimating resources
  How difficult will it be to do specific activities on this project?
  What is the organization’s history in doing similar activities?
  Are the required resources available?

## Slide 16: P4: Activity Duration Estimating
Duration vs. Effort
People doing the work should help create estimates, and an expert should review them
Instead of providing activity estimates as a discrete number, such as four weeks, it’s often helpful to create a three-point estimate

## Slide 17: In Reality…This is quite challenging
Stable Activities
  straightforward estimating
Dependent Activities
  amount needed for testing is dependent on a successful test or unsuccessful test.
  3-point estimates or analogous work well.
Uncertain Activities
  No previous precedence (complex projects)
  Start with 3-point estimate to set boundaries then use analogous to set actual estimate

## Slide 18: P5: Developing the Schedule
Ultimate goal is to create a realistic project schedule that provides a basis for monitoring project progress for the time dimension of the project
Input
1) Activity List & Attributes 2) Activity Resource Reqs 3) Resource Calendars 4) Schedule Diagrams 5) Duration Estimate 6) Scope Statement 7) Enterprise Factors 8) Org Process Assets
Output
1) Project Schedule 2) Schedule baseline 3) Schedule data 4) Updates to Project Docs
Tools/Techniques
1) Schedule Network analysis 2) Critical Path Method 3) Schedule Compression 4) What-if Scenarios 5) Resource Leveling 6) Critical Chain Method 7) Applying Leads/Lags 8) PM Software

## Slide 19: Project Time Management Processes

## Slide 20: Gantt Charts
Gantt charts provide a standard format for displaying project schedule information by listing project activities and their corresponding start and finish dates in a calendar format
Symbols include:
  A black diamond: a milestones
  Thick black bars: summary tasks
  Lighter horizontal bars: durations of tasks
  Arrows: dependencies between tasks

## Slide 21: Gantt Chart for Software Launch Project

## Slide 22: Milestones and Gantt Charts
Many people like to focus on meeting milestones, especially for large projects
Normally create milestone by entering tasks with a zero duration, or you can mark any task as a milestone
Milestones should follow the SMART Criteria
  1. Define milestones early and include in Gantt chart
  2. Keep milestones small and frequent
  3. The set of milestones must be all-encompassing
  4. Each milestone must be binary (either complete or incomplete)
  5. Carefully monitor the critical path

## Slide 23: Project Time Management Techniques
Critical Path Method
Critical Chain Scheduling
PERT

## Slide 24: Critical Path Method (CPM)
CPM is a network diagramming technique used to predict total project duration
  A critical path for a project is the series of activities that determines the earliest time by which the project can be completed
  Slack/float

## Slide 25: Determining the Critical Path

## Slide 26: Draw the Network (Arrow)
Activity | Initial Node | Final Node | Estimated Duration
A | 1 | 2 | 2
B | 2 | 3 | 2
C | 2 | 4 | 3
D | 2 | 5 | 4
E | 3 | 6 | 2
F | 4 | 6 | 3
G | 5 | 7 | 6
H | 6 | 8 | 2
I | 6 | 7 | 5
J | 7 | 8 | 1
K | 8 | 9 | 2
How long will it take to complete each path (how many?)
Which path is the critical path?

## Slide 27: Using Critical Path Analysis to Make Schedule Trade-offs
Free slack or free float
Total slack or total float
Forward pass
Backward pass

## Slide 28: Changes to the critical path
Techniques for shortening schedules
  Crashing Activities
  Fast tracking Activities
Updating Critical Path
  Continually update project schedule information to meet time goals for a project
  Critical path can change as you enter actual start and finish dates
  If you know the project completion date will slip, negotiate with the project sponsor

## Slide 29: PM Network: On the Right Track
Fast tracking almost always results in increased risk
Ask yourself questions
  Probability of producing expected benefits
  Resource Availability & complexity
  Buy-in – Is Everyone on Board?
  Can the PM manage it?

## Slide 30: Critical Chain Scheduling
Critical chain scheduling
  a method of scheduling that considers limited resources when creating a project schedule and includes buffers to protect the project completion date

## Slide 31: Buffers and Critical Chain
A buffer is additional time to complete a task
  In traditional estimates, people often add a buffer to each task and use it if it’s needed or not
Critical chain scheduling removes buffers from individual tasks and instead creates
  a project buffer or additional time added before the project’s due date
  feeding buffers or additional time added before tasks on the critical path

## Slide 32: Program Evaluation and Review Technique (PERT)
PERT is a network analysis technique used to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates
PERT weighted average =
optimistic time + 4X most likely time + pessimistic time
6

## Slide 33: PERT Example
What days should be included for the following activity:
Activity A:
Optimistic Estimate = 8 days
Most Likely Estimate = 10 days
Pessimistic Estimate = 24 days

## Slide 34: Final Notes on Project Schedule Development
Iterative Process
Review and revise the duration and resource estimates
  You want to create something that can get approved
Approved schedule will then act as the baseline to track progress

## Slide 35: PM Network: Time Tamers
Heathrow Airport
  Project control handbook
DOE - $3 billion over 70 projects
  Master schedule with critical path
Belleli Energy Srl
  Worst case scenarios and impact to critical path

## Slide 36: MC1: Schedule Control Suggestions
Perform reality checks on schedules
Allow for contingencies
Don’t plan for everyone to work at 100% capacity all the time
Hold progress meetings with stakeholders and be clear and honest in communicating schedule issues

## Slide 37: Controlling the Schedule
Goals are to know the status of the schedule, influence factors that cause schedule changes, determine that the schedule has changed, and manage changes when they occur
Reality Checks on Schedule
  First review the draft schedule or estimated completion date in the project charter
  Prepare a more detailed schedule with the team
  Make sure the schedule is realistic and followed
  Alert top management well in advance if there are schedule problems

## Slide 38: Using Software to Assist in Time Management
Software for facilitating communications helps people exchange schedule-related information
Decision support models help analyze trade-offs that can be made
Project management software can help in various time management areas

## Slide 39: Words of Caution on Using Project Management Software
Many people misuse project management software because they don’t understand important concepts and have not had training
You must enter dependencies to have dates adjust automatically and to determine the critical path
You must enter actual schedule information to compare planned and actual progress

## Slide 40: Chapter Summary
Project time management is often cited as the main source of conflict on projects, and most IT projects exceed time estimates
Main processes include
  Plan schedule management
  Define activities
  Sequence activities
  Estimate activity resources
  Estimate activity durations
  Develop schedule
  Control schedule